## Project_Overview
Parameter | Value
Project Title | DHA Smart Property Engine (PropSync DHA)
Target Repository | umarparvez94-Ch/Dha-app
Framework & Core Stack | Streamlit (Python), Google Sheets API (gspread), Pandas, Pillow, OpenPyXL
Design System | Google Stitch UI (Navy #0F172A, Emerald #10B981, Sky Blue #0EA5E9, Slate #F8FAFC)
Location Scope | DHA Lahore (Phases 1-13, EME, Rahwali, 9 Prism, 9 Town, Rahbar) & Nationwide DHAs
Implementation Date | August 2026
Status | In Progress / Active Refactor
Core Objective | Convert raw unstructured listings (WhatsApp, Camera OCR, Direct input) into block-wise Google Sheets inventory with live 3-view database and 1-click WhatsApp CRM.

## Feature_Roadmap
ID | Module | Feature | Details | Priority | Status | Target File
F-01 | UI/UX & Branding | Google Stitch Header & Agency Settings | Custom agency name modal/session state (e.g. Wali Muhammad Associates), real-time cloud sync pills, stats cards. | P0 (Critical) | Planned / Ready to Implement | App.py
F-02 | Data Ingestion | Multimodal Input Portal | Direct raw text box, rapid test preset buttons, st.camera_input for newspaper ads snapping, and file uploader. | P0 (Critical) | Planned / Ready to Implement | App.py
F-03 | NLP / Extraction | Smart Regex Parser Engine v3.0 | Extract Category (Selling/Buying/Rental), Property Type, Phase, Block, Size, Road Width (40ft-MB), Price, Phone, Tags. | P0 (Critical) | Planned / Ready to Implement | App.py
F-04 | Backend & Cloud | Dynamic Google Sheets Block Routing | Inspect Google Workbook, auto-create block-specific worksheet tabs (e.g. Block A, Block M) if missing, inject headers, append row. | P0 (Critical) | Planned / Ready to Implement | App.py
F-05 | Database Views | Categorized 3-Sheet Database View | Dedicated synchronized views per block: 1. Selling (Available), 2. Buying (Requirements), 3. Rental (Leases). | P0 (Critical) | Planned / Ready to Implement | App.py
F-06 | Search & Filters | Supreme Ultra-Smart Multi-Filter Search | Filter by City, Phase, Block, Size, Road Width, Tags (Corner, Park Facing, Excess Land, Direct Owner). | P1 (High) | Planned / Ready to Implement | App.py
F-07 | CRM & Fast Action | One-Click Copy Listing & Direct WhatsApp | Generate formatted WhatsApp text with agency branding and 1-click wa.me link with pre-filled inquiry message. | P1 (High) | Planned / Ready to Implement | App.py
F-08 | Storage & Settings | Google Service Account Setup Manager | Upload or paste service_account.json with automated validation and credential storage in .streamlit/secrets.toml. | P1 (High) | Planned / Ready to Implement | App.py

## Database_Schema
Col # | Column Name | Data Type | Description | Example
1 | Timestamp | Datetime | Auto timestamp (YYYY-MM-DD HH:MM:SS) | 2026-08-14 12:30:00
2 | Source | String | Origin of listing | WhatsApp Group
3 | Category | Enum | Selling ¦ Buying ¦ Rental | Selling
4 | Property Type | Enum | Plot ¦ House ¦ Commercial ¦ Apartment ¦ File | Plot
5 | City | String | Target City | Lahore
6 | Phase | String | DHA Phase (1-13, EME, Prism, etc.) | Phase 6
7 | Block | String | Target Block / Sector / CCA | Block M
8 | Size | String | Standardized size (Marla, Kanal, Sqft) | 1 Kanal
9 | Road Width | String | Road width (40ft, 60ft, 80ft, 100ft, 150ft, MB) | 80ft Road
10 | Features | String | Corner, Park Facing, Excess Land, Possession, Direct | Corner, Facing Park, Possession
11 | Price | String | Normalized price/demand string | 4.5 Crore
12 | Phone | String | Pakistani contact mobile number | 0300-1234567
13 | Agency | String | Agency / Agent Name | Wali Muhammad Associates
14 | Raw Listing Text | String | Full original unstructured text message | DHA Phase 6 Block M 1 Kanal plot for urgent sale demand 4.5 crore...

## Location_Taxonomy
City | Phase | Common Blocks | Special Attributes
Lahore | Phase 1 | Block A, B, C, D, E, F, G, H, J, K, L, M, N, P, CCA | Developed, Main Ghazi Road
Lahore | Phase 2 | Block Q, R, S, T, U, V, W, X, Y, Z, CCA | Developed, Lalik Jan Chowk
Lahore | Phase 3 | Block XX, Y, Z, Sector A-Z, Commercial Zone | Y Block Commercial, Sector Shops
Lahore | Phase 4 | Block AA, BB, CC, DD, EE, FF, GG, JJ, CCA | Civic Commercial Area, DD Commercial
Lahore | Phase 5 | Block A, B, C, D, E, F, G, H, J, K, L, M, CCA 1, CCA 2 | Bedian Road Access, Ring Road
Lahore | Phase 6 | Block A, B, C, D, E, F, G, H, J, K, L, M, N, CCA 1, CCA 2, Main Blvd | Main Boulevard 150ft, Rayya Golf Club
Lahore | Phase 7 | Block P, Q, R, S, T, U, V, W, X, Y, Z, CCA 1, CCA 2 | Direct Bedian & Barki Road Access
Lahore | Phase 8 (Ex-Park View & Air Avenue) | Block A, B, C, D, E, F, G, H, J, K, L, M, N, P, Q, R, S, T, U, V, W, X, Y, Z, CCA 1-3 | Airport Access, Commercial Broadway
Lahore | Phase 9 Prism | Block A, B, C, D, E, F, G, H, J, K, L, M, N, P, Q, R | Mega Project, 9 Drive, Ring Road Interchange
Lahore | Phase 9 Town | Block A, B, C, D, E | Compact, Highly Inhabited, 5 & 8 Marla
Lahore | Phase 10, 11 (Rahbar), 12 (EME), 13 | Sector A-Z, Block 1-10 | Emerging investment zones, Ring Road

## Sheets_Routing_Logic
Step # | Process Stage | Logic & Rule
1 | Message Parsing | Smart Regex Parser extracts 'Phase' and 'Block' from listing (e.g. 'Phase 6', 'Block M').
2 | Tab Name Determination | Tab name format: '{Phase} - {Block}' (e.g. 'Phase 6 - Block M') or 'Block M' if single phase context.
3 | Workbook Worksheet Check | Call gspread `spreadsheet.worksheets()` to check if the target tab exists.
4 | Auto-Create Worksheet | If tab missing: Execute `spreadsheet.add_worksheet(title=tab_name, rows=1000, cols=20)`.
5 | Header Row Injection | Inject standardized 14 column headers into Row 1 with formatting.
6 | Payload Insertion | Append extracted property row into the specific Block worksheet tab.
7 | Master Sync | Simultaneously append row to 'Master_Inventory' tab and local `data/properties.csv` for resilient offline access.